**Project Development Plan - Recruiter Ville**

Total Duration : 3 months

Total Resources : 5 (2 Designing + 3 Development)

Project Start Date : 18 Jan 2019

Project Delivery Date : 15 Apr 2019

Total Estimated Efforts : 900 Hrs

Total Phases : 6

Total Estimated Cost : Rs. 2,25,000

As per our discussion dated 16 Jan 2019, here we are providing the complete details and we are estimating to complete this project within 3 months in 6 phases. Each phase will be released every 15 days, so staging will be updated every 15 days. Once production has been setup completely we will be updating it every month.

**Software and Hardware Requirements:**

Hardware:

1. Windows server with configuration of 8 GB RAM and 100 GB Hard Disk.

Software:

1. SQL Server 2012 or higher version
2. Supported Browsers
3. Notepad++
4. .Net Framework 4.5
5. Visual Studio 2015 or higher version

**Milestones:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S No** | **Milestone** | **Tasks** | **Estimated Hours** | **Release Date** |
| 1 | Phase 1 | * Application Configuration * Website Designing(Logo and Home page) * Pricing * Registration and Login * User Profiles | 120 Hrs | 1st Feb 2019 |
| 2 | Phase 2 | * Website Designing(remaining all pages) * Vendor/Employer Management * Super User Configuration * Issues in 1st Phase | 150 Hrs | 15th Feb 2019 |
| 3 | Phase 3 | * Application Designing for Job Post, Upload Resumes * Candidate profile Creation * Resume upload * Issues in 2nd Phase | 150 Hrs | 1st Mar 2019 |
| 4 | Phase 4 | * Job Posting functionality * Job Sharing functionality * Resume basic Search * Issues in 3rd Phase | 150 hrs | 15th Mar 2019 |
| 5 | Phase 5 | * Resume Search(keyword search, Boolean search) * Sending Emails * Issues in 4th Phase * Super user side functionalities like managing users, resumes, candidate and emails. | 150 Hrs | 1st April 2019 |
| 6 | Phase 6 | * Payment gateways * Responsive Designing * Issues in total application * Remaining functionalities | 150 Hrs | 15th Apr 2019 |

**Pricing and Payments:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S No** | **Proposed Payment Term (in INR)** | **Description** | **Payment Date** | **Total Paid Till Term (in INR)** |
| 1 | 50,000 | Once accepted the Proposal and before going to start the work. | 19-Jan-2019 | 50,000 |
| 2 | 50,000 | After completing the Phase 2. | 15-Feb-2019 | 1,00,000 |
| 3 | 50,000 | After completing the Phase 4. | 15-Mar-2019 | 1,50,000 |
| 4 | 75,000 | After releasing the final phase. | 15-Apr-2019 | 2,25,000 |

**Note\*\*:**

* The estimations provided here are purely based on the freezed requirements. In case of any changes / enhancements in the functionality will be charged separately.
* Maintenance of the project will be provided for 1 year only. In case of any issues, they will be fixed during this period.
* Maintenance support after this period would be charged separately.